## Worksheet
Task | Start Date | End Date | Duration (Days) | Status
Requirement Analysis | 2024-03-01 | 2024-03-15 | 15 | Completed
Design Phase | 2024-03-16 | 2024-04-10 | 35 | In Progress
Development | 2024-04-11 | 2024-06-30 | 91 | Planned
Testing & Quality Assurance | 2024-07-01 | 2024-07-31 | 31 | Pending
Deployment & Review | 2024-08-01 | 2024-08-15 | 15 | Not Started