## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible Person | Status | Budget Allocation ($) | Actual Cost ($) | Variance
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Jane Smith | On Track | 5,000.00 | 4,800.00 |  | 200
Requirement Analysis | 2024-03-16 | 2024-04-15 | 30 | Mark Johnson | In Progress | 8,000.00 | 7,250.00 | 750
Design Phase | 2024-04-16 | 2024-05-31 | 45 | Lisa Chen | On Track | 12,000.00 | 11,800.00 | 200
Development & Testing | 2024-06-01 | 2024-08-31 | 90 | Robert Brown | Pending Start | 35,000.00 | - | -
Deployment & Review | 2024-09-01 | 2024-09-30 | 30 | Sophia Lee | Not Started | 6,500.00 | - | -
Total Budget ($) | - |  |  | $66,500.00 | - | $54,850.00 | $11,650.00 (Variance)