## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible Employee | Budget Allocated ($) | Actual Cost ($) | Variance ($)
Project Planning | 2024-03-01 | 2024-03-15 | 15 | On Track | Alice Johnson | 5,000 | 4,800 | 200
Design Development | 2024-03-16 | 2024-04-10 | 35 | On Track | Bob Smith | 12,000 | 11,500 | 500
Procurement & Sourcing | 2024-04-11 | 2024-05-05 | 35 | On Track | Charlie Lee | 8,000 | 7,950 | 50
Development & Testing | 2024-05-06 | 2024-07-15 | 71 | On Track | Diana Patel | 25,000 | 24,700 | 300
Deployment & Review | 2024-07-16 | 2024-08-31 | 46 | On Track | Evan Torres | 6,500 | 6,400 | 100