## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible | Budget Allocation | Actual Cost | Variance
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | On Track | Project Manager | $20,000 | $18,500 | +$1,500 (Under)
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | On Track | Business Analyst | $45,000 | $42,800 | +$2,200 (Under)
Design Phase | 2024-04-11 | 2024-05-15 | 45 | On Track | Lead Designer | $60,000 | $59,200 | +$800 (Under)
Development Phase | 2024-05-16 | 2024-08-31 | 117 | On Track | Development Team | $250,000 | $248,500 | +$1,500 (Under)
Testing & QA | 2024-09-01 | 2024-09-30 | 30 | On Track | QA Lead | $35,000 | $34,750 | +$250 (Under)
Deployment & Launch | 2024-10-01 | 2024-10-31 | 31 | On Track | IT Operations | $20,000 | $20,100 | -$100 (Over)