## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Budget Allocation ($) | Actual Spend ($)
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | John Smith | Completed | 10,000 | 9,850
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Sarah Lee | In Progress | 25,000 | 18,200
Design Phase | 2024-04-11 | 2024-05-30 | 60 | Michael Brown | Planned | 45,000 | 0
Development Phase | 2024-06-01 | 2024-08-31 | 90 | Lisa Wong | Not Started | 120,000 | 0
Testing & QA | 2024-09-01 | 2024-10-15 | 45 | David Kim | Planned | 30,000 | 0
Deployment & Training | 2024-10-16 | 2024-11-30 | 45 | Emma Clark | Not Started | 20,000 | 0
Total Budget: |  |  |  | $230,000
Total Actual Spend: |  |  |  | $38,050