## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible Person
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Completed | John Doe
Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | In Progress | Jane Smith
Design Phase | 2024-03-16 | 2024-04-05 | 21 | Planned | Alex Brown
Development Phase | 2024-04-06 | 2024-05-31 | 57 | Planned | Sarah Lee
Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | Planned | Mike Taylor
Deployment & Go-Live | 2024-07-01 | 2024-07-05 | 5 | Planned | Laura Kim
Post-Implementation Review | 2024-07-06 | 2024-07-10 | 5 | Planned | David Wong