## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status | Budget Allocated ($) | Actual Spend ($) | Variance ($)
Requirements Gathering | 2024-03-01 | 2024-03-15 | 15 | Product Team | Completed | 15,000 | 14,750 | 250
Design Phase | 2024-03-16 | 2024-04-10 | 25 | Design Team | In Progress | 20,000 | 18,500 | 1,500
Development Phase | 2024-04-11 | 2024-06-30 | 91 | Engineering Team | Not Started | 120,000 | 0 | 120,000
Testing & QA | 2024-07-01 | 2024-07-31 | 31 | QA Team | Not Started | 35,000 | 0 | 35,000
Deployment & Monitoring | 2024-08-01 | 2024-08-31 | 31 | Operations Team | Not Started | 25,000 | 0 | 25,000