## Worksheet
Date | Maintenance Task | Equipment/Asset ID | Location | Planned Duration (hrs) | Actual Duration (hrs) | Estimated Cost | Actual Cost | Variance (Actual - Estimated) | Approved By | Status
01/15/2024 | Lubrication of Conveyor Bearings | EQ-CON-004 | Warehouse B, Zone 3 | 2.5 | 2 | $180.00 | $165.00 | -$15.00 | J. Ramirez | Completed
01/20/2024 | Filter Replacement - HVAC System | HV-FLT-018 | Main Office, Floor 2 | 1.5 | 1.8 | $95.00 | $110.00 | +$15.00 | M. Chen | Completed
01/28/2024 | Electrical Inspection - Machine Line A | ML-A-ENG-101 | Production Floor, Area X | 4 | 5 | $420.00 | $510.00 | +$90.00 | T. Singh | In Progress
02/05/2024 | Pump Seal Replacement - Water System | WS-SEP-998 | Utility Closet, Basement | 3 | 3.2 | $240.00 | $250.00 | +$10.00 | L. Foster | Completed