## Worksheet
Project Activity | Budget Allocation (USD) | Actual Cost (USD) | Variance (USD) | Status | Responsible Party
Resource Planning & Forecasting | 25,000 | 24,800 | 200 | On Track | Finance Manager
Material Procurement | 75,000 | 74,500 | 500 | On Track | Procurement Officer
Labor Cost Management | 120,000 | 123,200 | -3,200 | Over Budget | Project Lead
Equipment Maintenance | 30,000 | 29,750 | 250 | On Track | Operations Team
Contingency & Risk Response | 15,000 | 12,800 | +2,200 | Under Budget | Risk Manager
Total Budget |  |  |  |  | 270,000
Total Actual Costs |  |  |  |  | 264,050
Total Variance |  |  |  |  | +5,950