## Worksheet
Date | Task | Responsible Person | Estimated Cost | Actual Cost | Variance (Actual - Estimated) | Status | Action Required
2023-10-01 | Material Procurement | John Doe | $5,000 | $4,800 |  | $200 (Under) | On Track | Review supplier quotes
2023-10-02 | Site Inspection | Jane Smith | $2,500 | $3,100 | $600 (Over) | At Risk | Request cost adjustment
2023-10-03 | Equipment Setup | Mike Johnson | $7,200 | $7,200 | $0 (On Budget) | On Track | Proceed with next phase
2023-10-04 | Labour Hours Tracking | Sarah Lee | $6,500 | $6,350 | $150 (Under) | On Track | Document for audit