## Worksheet
Task ID | Task Description | Responsible Party | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance | Status
P-001 | Project Initiation & Feasibility Study | John Smith | 2024-03-01 | 2024-03-15 | 15,000.00 | 14,850.00 | 150 | On Track
P-002 | Design Phase - Architecture & System ModelingSarah Lee | 2024-03-16 | 2024-04-30 | 75,000.00 | 73,950.00 | +1,050.00 | On Track
P-003 | Development Environment Setup | Mike Chen | 2024-05-01 | 2024-05-15 | 30,000.00 | 31,250.00 | -1,250.00 | At Risk
P-004 | Development & Coding Phase (Phase 1) | Alice Wang | 2024-05-16 | 2024-07-31 | 250,000.00 | 248,750.00 | +1,250.00 | On Track
P-005 | Testing & Quality Assurance | Robert Davis | 2024-08-01 | 2024-09-15 | 85,000.00 | 86,350.00 | -1,350.00 | On Track
Total Budget |  |  |  | 455,000.00 | Total Actual Cost | 456,350.00 | Overall Variance | +1,350.00