## Worksheet
Task ID | Task Name | Responsible Party | Start Date | End Date | Budget Allocation (USD) | Actual Cost (USD) | Variance (USD) | Status | Cost Control Measures
P001 | Project Kickoff Meeting | Project Manager | 2024-03-15 | 2024-03-15 | 5,000.00 | 4,850.00 | 150 | Completed | Approved budget; attendance tracked.
P002 | Requirements Gathering | Business Analysts | 2024-03-16 | 2024-04-15 | 15,000.00 | 14,750.00 | 250 | In Progress | Weekly cost reviews; scope freeze scheduled.
P003 | Design Phase Finalization | UX & UI Team | 2024-04-16 | 2024-05-15 | 30,000.00 | 31,250.00 | -1,250.00 | In Progress | Identified overruns; revised timeline and budget approved.
P004 | Development & Coding | Software Development Team | 2024-05-16 | 2024-07-31 | 120,000.00 | 118,750.00 | +1,250.00 | In Progress | Code reviews implemented; change control process enforced.
P005 | Testing & Quality Assurance | QA Engineers | 2024-08-01 | 2024-08-31 | 25,000.00 | 24,950.00 | 50 | Pending | Test automation adopted; cost tracking via JIRA.
P006 | Deployment & Go-Live | DevOps Team | 2024-09-01 | 2024-09-15 | 15,000.00 | 14,850.00 | 150 | Planned | Daily cost monitoring; rollback plan in place.
P007 | Post-Implementation Review | Project Management Office | 2024-09-16 | 2024-09-30 | 10,000.00 | 9,750.00 | 250 | Planned | Cost variance analysis completed; lessons learned documented.