## Worksheet
Task | Responsible | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance | Status
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | 15,000 | 14,850 | +150 (Under Budget) | On Track
Requirements Gathering | Business Analyst | 2024-03-16 | 2024-04-10 | 25,000 | 24,750 | +250 (Under Budget) | On Track
Design Phase | UI/UX Designer | 2024-04-11 | 2024-05-05 | 35,000 | 34,950 | +100 (Under Budget) | On Track
Development Phase | Software Developers | 2024-05-06 | 2024-07-15 | 150,000 | 148,200 | +1,800 (Under Budget) | On Track
Testing & QA | QA Team | 2024-07-16 | 2024-08-10 | 35,000 | 34,650 | +350 (Under Budget) | On Track
Deployment | DevOps Engineer | 2024-08-11 | 2024-08-15 | 15,000 | 15,000 | +0 (On Budget) | Completed
Post-Implementation Review | Project Manager | 2024-08-16 | 2024-08-31 | 10,000 | 9,850 | +150 (Under Budget) | On Track
Total Budget (USD) |  |  |  | 275,000 | 273,400 | +1,600 (Under Budget)