## Worksheet
Task ID | Task Description | Responsible Party | Start Date | End Date th> | Budget Allocation (USD) | Actual Spend (USD) | Variance (USD) | Status | Approval Status
P-001 | Project Initiation & Feasibility Study | Project Director | 2024-03-15 | 2024-03-31 | $50,000.00 | $48,750.00 | $1,250.00 (Under) | Completed | Approved
P-002 | Market Research & Analysis | Research Lead | 2024-04-01 | 2024-04-15 | $35,000.00 | $36,250.00 | -$1,250.00 (Over) | In Progress | Pending Review
P-003 | Design & Prototyping Phase | Design Team | 2024-05-01 | 2024-06-30 | $120,000.00 | $118,500.00 | $1,500.00 (Under) | On Track | Approved
P-004 | Development & Testing Phase | Engineering Team | 2024-07-01 | 2024-10-31 | $300,000.00 | $295,650.00 | $4,350.00 (Under) | Planned | Approved
P-005 | Deployment & Training | Operations Manager | 2024-11-01 | 2024-12-31 | $85,000.00 | $83,950.00 | $1,050.00 (Under) | Not Started | Pending Approval