## Worksheet
Task | Responsible | Start Date | End Date | Estimated Cost | Actual Cost | Variance | Status
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | $15,000 | $14,800 | +$200 (under budget) | On Track
Requirements Gathering | Business Analyst | 2024-03-16 | 2024-04-10 | $25,000 | $25,500 | -$500 (over budget) | At Risk
Design Phase | UX Designer | 2024-04-11 | 2024-05-05 | $30,000 | $31,200 | -$1,200 (over budget) | On Track
Development | Engineering Team | 2024-05-06 | 2024-07-15 | $180,000 | $178,500 | +$1,500 (under budget) | On Track
Testing & QA | QA Lead | 2024-07-16 | 2024-08-10 | $35,000 | $34,800 | +$200 (under budget) | On Track
Deployment | Operations Team | 2024-08-11 | 2024-08-15 | $15,000 | $15,000 | $0 (on budget) | On Track
Total Project Cost Estimate |  |  | $280,000 | $279,100 | +$900 (under budget) | Overall: Cost Controlled & Within Budget