## Worksheet
Task | Responsible | Start Date | End Date | Budget (USD) | Actual Cost | Variance | Status
Project Initiation | John Doe | 01/01/2024 | 01/15/2024 | 5,000 | 4,800 | 200 | On Track
Requirements Gathering | Jane Smith | 01/16/2024 | 02/14/2024 | 8,000 | 7,500 | 500 | On Track
Design Phase | Mike Johnson | 02/15/2024 | 03/20/2024 | 15,000 | 14,750 | 250 | On Track
Development Phase | Sarah Lee | 03/21/2024 | 05/31/2024 | 40,000 | 39,600 | 400 | On Track
Testing & QA | David Brown | 06/01/2024 | 06/30/2024 | 7,500 | 7,350 | 150 | On Track
Deployment & Review | Linda Taylor | 07/01/2024 | 07/15/2024 | 3,000 | 3,100 | -100 | On Track