## Worksheet
Task | Responsible Party | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Variance | Status | Review Date
Project Initiation & Feasibility Study | Project Manager | 01/Jan/2024 | 31/Jan/2024 | 50,000 | 48,750 | +1,250 (Under Budget) | On Track | 05/Feb/2024
Requirements Gathering & Analysis | Business Analysts | 01/Feb/2024 | 28/Feb/2024 | 75,000 | 73,500 | +1,500 (Under Budget) | On Track | 15/Feb/2024
Design & Architecture Phase | Lead Architect | 01/Mar/2024 | 30/Mar/2024 | 95,000 | 96,800 | -1,800 (Over Budget) | At Risk | 25/Mar/2024
Development & Coding Phase | Engineering Team | 01/Apr/2024 | 30/Apr/2024 | 300,000 | 295,400 | +4,600 (Under Budget) | On Track | 30/Apr/2024
Testing & Quality Assurance | QA Lead | 01/May/2024 | 31/May/2024 | 65,000 | 64,850 | +150 (Under Budget) | On Track | 31/May/2024
Deployment & Go-Live | IT Operations | 01/Jun/2024 | 05/Jun/2024 | 30,000 | 30,150 | -150 (Over Budget) | On Track | 06/Jun/2024
Post-Implementation Review & Optimization | Project Manager & Stakeholders | 06/Jul/2024 | 30/Jul/2024 | 40,000 | 39,750 | +250 (Under Budget) | On Track | 31/Jul/2024