## Worksheet
Task ID | Task Name | Responsible | Start Date | End Date | Budget Allocation (USD) | Actual Cost (USD) | Variance (%) | Status | Cost Control Action
P-001 | Project Initiation & Scope Finalization | John Smith | 2024-03-15 | 2024-03-31 | $50,000 | $48,750 | +1.5% | On Track | Review scope with stakeholders.
P-002 | Market Research & Feasibility Study | Sarah Lee | 2024-04-01 | 2024-04-15 | $75,000 | $76,250 | -1.6% | At Risk | Adjust budget by 2% and reallocate to design.
P-003 | Product Design & Prototyping | David Chen | 2024-04-16 | 2024-05-31 | $150,000 | $148,500 | +1.2% | On Track | Proceed with prototype testing as scheduled.
P-004 | Supplier Sourcing & Procurement | Linda Wong | 2024-05-01 | 2024-06-15 | $90,000 | $93,750 | -3.8% | Over Budget | Conduct cost audit and renegotiate contracts.
P-005 | Development & Testing Phase | Michael Torres | 2024-06-16 | 2024-08-31 | $300,000 | $295,875 | +1.4% | On Track | Monitor weekly cost reports and maintain control.