## Worksheet
Month | Budgeted Cost | Actual Cost | Variance | Variance (%) | Cost Control Action | Responsible Party
January | $150,000 | $148,500 | -$1,500 | -1.0% | Review procurement strategy | Finance Manager
February | $160,000 | $162,200 | +$2,200 | +1.4% | Reassess vendor contracts | Project Director
March | $170,000 | $169,800 | -$200 | -0.1% | Maintain current controls | Cost Analyst
April | $180,000 | $179,500 | -$500 | -0.3% | Implement expense tracking tools | Operations Lead
May | $190,000 | $192,100 | +$2,100 | +1.1% | Conduct cost review meeting | Project Manager