## Worksheet
Project Phase | Activity | Responsible Party | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Variance (USD) | Status
Initiation | Feasibility Study | Project Director | 2024-01-15 | 2024-01-31 | 50,000 | 48,750 | +1,250 | On Track
Planning | Resource Allocation | Project Manager | 2024-02-01 | 2024-02-15 | 75,000 | 73,500 | +1,500 | On Track
Execution | Development Phase 1 | Development Team | 2024-03-01 | 2024-05-31 | 350,000 | 345,875 | +4,125 | On Track
Review & Control | Cost Performance Review | Finance Officer | 2024-06-15 | 2024-06-30 | 50,000 | 49,850 | 150 | On Track
Total Budget (USD) | — |  |  | 525,000 | — | 477,975 | +47,025 | Overall Status: On Track