## Worksheet
Task | Responsible | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance (USD) | Status
Project Initiation | Project Manager | 2024-01-15 | 2024-01-30 | 15,000 | 14,850 | 150 | On Track
Requirements Gathering | Business Analysts | 2024-02-01 | 2024-03-15 | 30,000 | 31,250 | -1,250 | At Risk
Design Phase | UX & Architecture Team | 2024-03-16 | 2024-04-30 | 45,000 | 44,750 | 250 | On Track
Development Phase | Software Developers | 2024-05-01 | 2024-07-31 | 180,000 | 178,500 | +1,500 | On Track
Testing & QA | QA Team | 2024-08-01 | 2024-08-31 | 25,000 | 24,950 | 50 | On Track
Deployment & Go-Live | Operations Team | 2024-09-01 | 2024-09-30 | 15,000 | 15,150 | -150 | On Track