## Worksheet
Task | Responsible Party | Start Date | End Date | Budget Allocation | Actual Cost | Variance | Status
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | $5,000 | $4,800 | +$200 (Under Budget) | On Track
Requirements Gathering | Business Analyst | 2024-03-16 | 2024-04-10 | $8,500 | $8,350 | +$150 (Under Budget) | On Track
Design Phase | UX Designer | 2024-04-11 | 2024-05-05 | $12,000 | $12,450 | -$450 (Over Budget) | At Risk
Development & Testing | Engineering Team | 2024-05-06 | 2024-07-15 | $45,000 | $43,800 | +$1,200 (Under Budget) | On Track
Go-Live & Training | Operations Lead | 2024-07-16 | 2024-07-30 | $7,500 | $7,450 | +$50 (Under Budget) | On Track