## Worksheet
Task | Responsible Party | Start Date | End Date | Budget Allocation ($) | Actual Cost ($) | Variance ($) | Status
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | 15,000 | 14,850 | 150 | On Track
Requirements Gathering | Business Analysts | 2024-03-16 | 2024-04-10 | 35,000 | 34,750 | 250 | On Track
Design Phase | Design Team | 2024-04-11 | 2024-05-15 | 60,000 | 62,300 | -2,300 | Over Budget
Development Phase | Development Team | 2024-05-16 | 2024-07-31 | 180,000 | 178,500 | +1,500 | On Track
Testing & QA | QA Team | 2024-08-01 | 2024-08-31 | 35,000 | 34,950 | 50 | On Track
Deployment & Training | IT Operations & Trainers | 2024-09-01 | 2024-09-30 | 25,000 | 25,150 | -150 | On Track
Total Budget Allocated ($) | [5 empty] | 340,000 | 341,550 | +1,550 | Overall Variance Status: Slight Overrun