## Worksheet
Task | Responsible | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Variance | Status
Market Research & Analysis | Marketing Team | 2024-03-01 | 2024-03-15 | 5,000 | 4,800 | +200 (Under Budget) | On Track
Product Design & Prototyping | Design Team | 2024-03-16 | 2024-04-10 | 8,500 | 8,350 | +150 (Under Budget) | On Track
Development & Coding | Engineering Team | 2024-04-11 | 2024-06-30 | 35,000 | 32,750 | +2,250 (Under Budget) | On Track
QA Testing & Validation | QA Team | 2024-07-01 | 2024-07-31 | 6,000 | 5,950 | +50 (Under Budget) | On Track
Launch & Marketing Campaign | Marketing Team | 2024-08-01 | 2024-08-31 | 15,000 | 14,750 | +250 (Under Budget) | On Track