## Worksheet
Task | Responsible | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance | Status
Project Kickoff Meeting | Project Manager | 2024-03-01 | 2024-03-01 | 5,000 | 4,800 | +200 (Under Budget) | Completed
Requirements Gathering | Business Analyst | 2024-03-02 | 2024-03-15 | 15,000 | 14,750 | +250 (Under Budget) | On Track
Design Phase | UX/UI Team | 2024-03-16 | 2024-04-10 | 30,000 | 29,500 | +500 (Under Budget) | On Track
Development Phase | Engineering Team | 2024-04-11 | 2024-06-30 | 120,000 | 118,750 | +1,250 (Under Budget) | On Track
Testing & Quality Assurance | QA Team | 2024-07-01 | 2024-07-31 | 25,000 | 24,950 | +50 (Under Budget) | Completed
Deployment & Training | Operations Team | 2024-08-01 | 2024-08-15 | 15,000 | 14,800 | +200 (Under Budget) | Completed
Total Budget: |  |  | 210,000 | 208,450 | +1,550 (Under Budget) | Cost Control Achieved