## Worksheet
Task | Responsible Team | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance | Status | Review Date
Requirement Analysis | Product Planning Team | 2024-03-01 | 2024-03-15 | 15,000 | 14,200 | +800 (Under Budget) | On Track | 2024-03-16
Design Phase | UX & UI Design Team | 2024-03-16 | 2024-04-10 | 35,000 | 34,850 | +150 (Under Budget) | On Track | 2024-04-11
Development Build | Engineering Team | 2024-04-11 | 2024-06-30 | 120,000 | 118,500 | +1,500 (Under Budget) | On Track | 2024-06-31
Testing & QA | QA & Testing Team | 2024-07-01 | 2024-07-31 | 25,000 | 24,650 | +350 (Under Budget) | On Track | 2024-08-01
Deployment & Go-Live | Operations Team | 2024-08-01 | 2024-08-15 | 15,000 | 15,200 | -200 (Over Budget) | On Track | 2024-08-16