## Worksheet
Task | Responsible Party | Start Date | End Date | Budget Allocation | Actual Spend | Variance | Status
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | $5,000 | $4,850 | $150 (Under) | On Track
Resource Planning | HR & Finance Team | 2024-03-16 | 2024-04-05 | $7,500 | $7,320 | $180 (Under) | On Track
Design Phase | Design Team | 2024-04-06 | 2024-05-31 | $15,000 | $14,950 | $50 (Under) | On Track
Development & Testing | Engineering Team | 2024-06-01 | 2024-08-31 | $50,000 | $49,875 | $125 (Under) | On Track
Deployment & Training | Operations & Support Team | 2024-09-01 | 2024-10-31 | $10,000 | $9,750 | $250 (Under) | On Track
Total Budget |  |  | $87,500 | $86,900 | $600 (Under) | Overall Status: Cost Control Achieved