## Worksheet
Project Plan – Weekly Cost Control (Style/Version: Weekly)
Week | Project Phase | Budget Allocation (USD) | Actual Costs (USD) | Variance (USD) | Variance % | Cost Control Actions Taken th> | Status th>
Week 1 | Initiation & Planning | 50,000.00 | 48,250.00 |  | +1,750.00 | +3.5% | Reviewed scope and finalized resource plan. | On Track
Week 2 | Design & Requirements Finalization | 80,000.00 | 79,500.00 | 500 | +1.2% | Conducted cost-benefit analysis and approved design. | On Track
Week 3 | Development Phase (Phase 1) | 120,000.00 | 118,750.00 | +1,250.00 | +1.1% | Implemented daily cost tracking; adjusted sprint budgets. | On Track
Week 4 | Development Phase (Phase 2) | 150,000.00 | 149,250.00 | 750 | +1.3% | Added overtime monitoring; approved vendor cost review. | On Track
Week 5 | Testing & Quality Assurance | 60,000.00 | 59,800.00 | 200 | +1.2% | Reduced test environment costs via cloud optimization. | On Track