## Worksheet
Item | Description | Estimated Cost | Actual Cost | Variance | Status
1 | Project Initiation & Planning | $15,000 | $14,200 | +$800 (Under Budget) | On Track
2 | Resource Acquisition | $45,000 | $47,500 | -$2,500 (Over Budget) | At Risk
3 | Development Phase | $120,000 | $118,000 | +$2,000 (Under Budget) | On Track
4 | Testing & Quality Assurance | $30,000 | $28,500 | +$1,500 (Under Budget) | On Track
5 | Deployment & Training | $25,000 | $26,000 | -$1,000 (Over Budget) | At Risk
Total Estimated Cost |  |  | $235,000 | $234,200