## Worksheet
Project Name | Budget (USD) | Actual Expenditure (USD) | Variance (USD) | Variance % | Status | Responsible Person | Review Date
Phase I Development | 500,000 | 475,000 | -25,000 | -5.0% | On Track | Jane Doe | 2024-03-30
Phase II Testing | 300,000 | 325,000 | +25,000 | +8.3% | At Risk | John Smith | 2024-04-15
Phase III Deployment | 650,000 | 648,500 | -1,500 | -0.2% | On Track | Lisa Chen | 2024-05-05
Post-Deployment Review | 50,000 | 49,200 | -800 | -1.6% | On Track | Mark Taylor | 2024-05-30