## Worksheet
Date | Project Name | Budget Allocated | Actual Expenditure | Variance (Actual - Budget) | Status | Remarks
2023-10-01 | Website Redesign | $15,000 | $14,200 | -$800 | On Track | Minor delays in development phase.
2023-10-02 | Mobile App Development | $25,000 | $27,500 | +$2,500 | Over Budget | Third-party API costs exceeded estimates.
2023-10-03 | Marketing Campaign | $10,000 | $9,800 | -$200 | On Track | All targets achieved; budget underutilized.
2023-10-04 | Server Infrastructure Upgrade | $30,000 | $31,200 | +$1,200 | Over Budget | Unexpected hardware failure required additional procurement.