## Worksheet
Task/Activity | Budget Allocation (USD) | Actual Cost (USD) | Variance (USD) | Variance % | Status | Responsible Person | Approved By | Date Approved
Project Initiation & Feasibility Study | 50,000 | 48,200 | +1,800 | +3.6% | On Track | J. Smith | M. Johnson | 2024-03-15
Design & Planning Phase | 120,000 | 125,600 | -5,600 | -4.7% | At Risk | A. Lee | M. Johnson | 2024-04-05
Procurement & Vendor Selection | 80,000 | 82,400 | -2,400 | -3.0% | At Risk | R. Kim | T. Brown | 2024-05-10
Development & Implementation | 450,000 | 442,800 | +7,200 | +1.6% | On Track | L. Davis | M. Johnson | 2024-06-20
Testing & Quality Assurance | 60,000 | 58,900 | +1,100 | +1.8% | On Track | S. Patel | T. Brown | 2024-07-08
Project Closure & Reporting | 30,000 | 29,500 | 500 | +1.7% | On Track | J. Smith | M. Johnson | 2024-08-15