## Worksheet
Task | Estimated Cost | Actual Cost | Variance (Actual - Estimated) | Status | Notes
Project Planning | $15,000 | $14,500 | -$500 | On Track | Completed ahead of schedule.
Design Development | $30,000 | $32,200 | +$2,200 | Over Budget | Additional revisions required.
<Procurement & Sourcing | $25,000 | $24,800 | -$200 | On Track | All vendors confirmed.
Development Phase | $100,000 | $98,500 | -$1,500 | On Track | No major deviations.
Testing & Quality Assurance | $20,000 | $21,300 | +$1,300 | Over Budget | Extended testing cycles.
Deployment & Training | $18,000 | $17,900 | -$100 | On Track | All staff trained.