## Worksheet
Task | Budget (USD) | Actual Cost (USD) | Variance | Status | Owner
Project Initiation | 5,000 | 4,800 | +200 (Under Budget) | On Track | Alex Morgan
Market Research | 3,500 | 3,650 | -150 (Over Budget) | At Risk | Jamie Lee
Design Development | 8,000 | 7,950 | +50 (Under Budget) | On Track | Samira Patel
Development Phase | 25,000 | 24,700 | +300 (Under Budget) | On Track | Marcus Kim
Testing & QA | 4,200 | 4,100 | +100 (Under Budget) | On Track | Tina Wu
Deployment | 2,000 | 2,100 | -100 (Over Budget) | At Risk | Ryan Foster
Total Budget: |  |  | 57,700 | Cost Control Summary
Total Actual: |  |  | 54,450 | Overall Savings: $3,250