## Worksheet
Task ID | Task Description | Responsible Person | Start Date | End Date | Budget Allocated (USD) | Actual Cost (USD) | Variance (USD) | Status
P-001 | Project Initiation & Feasibility Study | J. Smith | 2024-03-01 | 2024-03-15 | 15,000.00 | 13,850.00 |  | +1,150.00 | On Track
P-002 | Requirements Gathering & Analysis | A. Johnson | 2024-03-16 | 2024-04-30 | 25,000.00 | 24,575.00 | 425 | On Track
P-003 | Design Phase & Architecture Review | M. Lee | 2024-05-01 | 2024-05-31 | 35,000.00 | 36,890.00 | -1,890.00 | Over Budget
P-004 | Development & Coding Phase | S. Williams | 2024-06-01 | 2024-08-31 | 120,000.00 | 115,675.00 | +4,325.00 | On Track
P-005 | Testing & Quality Assurance | T. Brown | 2024-09-01 | 2024-10-31 | 28,500.00 | 27,985.00 | 515 | On Track