## Worksheet
Item | Description | Budget (USD) | Actual (USD) | Variance (USD) | Status
Project Initiation | Feasibility study, stakeholder analysis, and requirement gathering | 25,000 | 24,500 | -500 | On Track
Resource Allocation | Assignment of personnel and equipment to project phases | 40,000 | 39,200 | -800 | On Track
Design Phase | Development of technical designs and specifications | 60,000 | 58,750 | -1,250 | On Track
Development & Testing | Coding, integration, and quality assurance testing | 120,000 | 124,500 | +4,500 | Over Budget
Deployment & Go-Live | System rollout, user training, and data migration | 30,000 | 29,800 | -200 | On Track
Post-Implementation Review | Performance evaluation, lessons learned, and closure planning | 10,000 | 9,900 | -100 | On Track