## Worksheet
Category | Item | Estimated Cost (USD) | Actual Cost (USD) | Variance (USD) | Status
Project Planning | Scope Definition | 5,000 | 4,800 | 200 | On Track
Project Planning | Risk Assessment | 3,500 | 3,650 | -150 | On Track
Design & Development | UI/UX Design | 10,000 | 9,800 | 200 | On Track
Design & Development | Frontend Development | 15,000 | 16,200 | -1,200 | Over Budget
Testing & Deployment | QA Testing | 4,000 | 3,950 | 50 | On Track
Testing & Deployment | Deployment | 2,500 | 2,450 | 50 | On Track
Total Estimated Cost |  |  | 40,000
Total Actual Cost |  |  | 40,850 | 850