## Worksheet
Task | Start Date | End Date | Responsible Party | Budget Allocation ($) | Actual Cost ($) | Variance ($) | Status | Cost Control Action
Project Initiation & Feasibility Study | 2024-03-01 | 2024-03-15 | Project Manager | 50,000 | 48,500 | +1,500 (Under Budget) | On Track | Monthly review of scope and budget alignment.
Requirements Gathering & Analysis | 2024-03-16 | 2024-04-30 | Business Analysts | 75,000 | 73,200 | +1,800 (Under Budget) | On Track | Review stakeholder feedback weekly.
Design & Prototyping Phase | 2024-05-01 | 2024-06-15 | Design Team | 90,000 | 92,150 | -2,150 (Over Budget) | At Risk | Reassess design scope; request cost mitigation plan.
Development & Coding Phase | 2024-06-16 | 2024-08-31 | Engineering Team | 350,000 | 345,750 | +4,250 (Under Budget) | On Track | Conduct weekly cost audits and code reviews.
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | QA Team | 65,000 | 64,850 | +150 (Under Budget) | On Track | Monitor defect rates and rework costs.
Deployment & Go-Live | 2024-10-16 | 2024-10-31 | Operations Team | 40,000 | 39,500 | +500 (Under Budget) | On Track | Ensure minimal downtime and rollback plan in place.