## Worksheet
Activity | Start Date | End Date | Responsible Party | Budget Allocation (USD) | Actual Spend (USD) | Variance (USD) | Status | Control Action
Project Initiation & Feasibility Study | 2024-01-15 | 2024-01-31 | Project Director | 50,000 | 48,750 | +1,250 | On Track | Review budget assumptions
Requirements Gathering & Analysis | 2024-02-01 | 2024-03-15 | Business Analysts | 75,000 | 74,200 | 800 | On Track | Monitor scope changes
Design Phase (UI/UX & Architecture) | 2024-03-16 | 2024-05-10 | Design Team | 90,000 | 89,500 | 500 | On Track | Verify design cost against budget
Development & Coding Phase | 2024-05-11 | 2024-08-30 | Engineering Team | 350,000 | 348,750 | +1,250 | On Track | Conduct weekly cost reviews
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | QA Team | 60,000 | 59,800 | 200 | On Track | Ensure no scope creep
Deployment & Go-Live | 2024-10-16 | 2024-10-31 | Operations Team | 30,000 | 29,500 | 500 | On Track | Final cost verification