## Worksheet
Activity | Start Date | End Date | Responsible Party | Budget Allocation (USD) | Status | Cost Variance
Project Initiation | 01/01/2024 | 01/31/2024 | Project Manager | 50,000.00 | On Track | $0.00
Scope Definition & Approval | 02/01/2024 | 02/15/2024 | Business Analyst | 35,000.00 | On Track | $250.00 (Under)
Resource Planning | 03/01/2024 | 03/31/2024 | HR & Finance Team | 60,000.00 | On Track | $1,250.00 (Under)
Design & Prototyping | 04/01/2024 | 05/31/2024 | Design Team | 95,000.00 | On Track | $5,400.00 (Under)
Development Phase | 06/01/2024 | 08/31/2024 | Engineering Team | 375,000.00 | On Track | $18,200.00 (Under)
Testing & Quality Assurance | 09/01/2024 | 10/31/2024 | QA Team | 75,000.00 | On Track | $3,100.00 (Under)
Deployment & Go-Live | 11/01/2024 | 11/30/2024 | IT Operations | 45,000.00 | On Track | $0.00
Post-Implementation Review | 12/01/2024 | 12/31/2024 | Project Steering Committee | 30,000.00 | On Track | $1,850.00 (Under)