## Worksheet
Activity | Start Date | End Date | Responsible Party | Budget Allocation (USD) | Status | Cost Variance
Project Initiation | 2024-01-15 | 2024-01-31 | Project Manager | 50,000.00 | On Track | $0.00
Requirements Gathering | 2024-02-01 | 2024-03-15 | Business Analysts | 75,000.00 | On Track | $1,250.00 (Under)
Design Phase | 2024-03-16 | 2024-05-31 | UI/UX Team | 120,000.00 | On Track | $2,800.00 (Under)
Development | 2024-06-01 | 2024-09-30 | Engineering Team | 500,000.00 | On Track | $15,300.00 (Over)
Testing & QA | 2024-10-01 | 2024-11-30 | QA Team | 85,000.00 | On Track | $500.00 (Under)
Deployment & Go-Live | 2024-12-01 | 2024-12-31 | Operations Team | 30,000.00 | On Track | $0.00