## Worksheet
Task | Responsible | Start Date | End Date | Duration (Days) | Budget Allocation ($) | Actual Cost ($) | Variance ($) | Status | Progress (%) | Risk Level | Review Date
Project Initiation & Feasibility Study | Project Manager | 2024-03-01 | 2024-03-15 | 15 | 15,000 | 14,200 | 800 | On Track | 95% | Low | 2024-03-16
Requirement Gathering & Analysis | Business Analysts | 2024-03-16 | 2024-04-10 | 35 | 30,000 | 29,850 | 150 | On Track | 92% | Low | 2024-04-11
Design & Architecture Development | Senior Architects | 2024-04-11 | 2024-05-15 | 45 | 50,000 | 49,750 | 250 | On Track | 88% | Medium | 2024-05-16
Development & Coding Phase | Software Engineers | 2024-05-16 | 2024-07-31 | 86 | 120,000 | 118,500 | +1,500 | On Track | 76% | High | 2024-08-01
Testing & Quality Assurance | QA Team | 2024-08-01 | 2024-08-31 | 31 | 25,000 | 24,900 | 100 | On Track | 97% | Low | 2024-09-01
Deployment & Go-Live | Operations Team | 2024-09-01 | 2024-09-15 | 15 | 18,000 | 17,800 | 200 | On Track | 100% | Low | 2024-09-16
Post-Implementation Review & Optimization | Project Manager & Analysts | 2024-09-16 | 2024-10-31 | 46 | 20,000 | 19,500 | 500 | On Track | 82% | Medium | 2024-11-01