## Worksheet
Task | Start Date | End Date | Responsible Person | Budget Allocation (USD) | Actual Cost (USD) | Variance | Status
Project Initiation | 2024-01-01 | 2024-01-15 | John Smith | 5,000 | 4,800 | +200 (Under Budget) | On Track
Requirements Gathering | 2024-01-16 | 2024-02-05 | Sarah Lee | 8,000 | 7,950 | +50 (Under Budget) | On Track
Design Phase | 2024-02-06 | 2024-03-15 | Mike Chen | 15,000 | 14,800 | +200 (Under Budget) | On Track
Development & Testing | 2024-03-16 | 2024-05-31 | Lisa Wong | 45,000 | 46,200 | -1,200 (Over Budget) | Delayed (Risk)
Deployment & Training | 2024-06-01 | 2024-06-30 | David Kim | 10,000 | 9,850 | +150 (Under Budget) | On Track
Total Budget: |  |  |  | 83,000 | 73,600 | +9,400 (Under Budget)