## Worksheet
Task | Start Date | End Date | Responsible Employee | Budget Allocated (USD) | Actual Spend (USD) | Variance (USD) | Status
Project Initiation & Planning | 2024-01-15 | 2024-02-10 | Sarah Johnson | 15,000.00 | 14,850.00 | 150 | On Track
Design & Requirements Finalization | 2024-02-11 | 2024-03-15 | Mike Thompson | 25,000.00 | 24,975.00 | 25 | On Track
Development Phase (Phase 1) | 2024-03-16 | 2024-05-31 | Lisa Chen | 75,000.00 | 74,625.00 | 375 | On Track
Testing & Quality Assurance | 2024-06-01 | 2024-07-15 | David Ruiz | 30,000.00 | 31,250.00 | -1,250.00 | Minor Overrun
Deployment & Go-Live | 2024-07-16 | 2024-08-10 | Emma Park | 10,000.00 | 9,850.00 | 150 | On Track
Post-Deployment Review & Closure | 2024-08-11 | 2024-08-31 | Sarah Johnson | 5,000.00 | 4,950.00 | 50 | On Track
Total Budget Allocated |  |  | 150,000.00 | 150,675.00 | 675 | Overall Variance: +$675 (Minor Overrun)