## Worksheet
Activity | Start Date | End Date | Responsible Party | Budget Allocation ($) | Actual Cost ($) | Variance ($) | Status | Risk Level | Cost Control Action
Project Initiation & Feasibility Study | 01/01/2024 | 02/15/2024 | Project Manager | 50,000.00 | 48,750.00 | +1,250.00 | On Track | Low | None required
Scope Definition & Requirements Gathering | 02/16/2024 | 03/31/2024 | Business Analysts | 75,000.00 | 72,950.00 | +2,050.00 | On Track | Medium | Monitor scope changes
Design & Technical Specifications | 04/01/2024 | 05/30/2024 | Engineering Team | 150,000.00 | 148,250.00 | +1,750.00 | On Track | Low | Review cost assumptions
Procurement & Vendor Selection | 06/01/2024 | 07/15/2024 | Procurement Officer | 95,000.00 | 112,300.00 | -17,300.00 | At Risk | High | Initiate cost recovery review
Development & Implementation | 07/16/2024 | 09/30/2024 | Development Team | 350,000.00 | 345,675.00 | +4,325.00 | On Track | Medium | Perform weekly cost audits
Testing & Quality Assurance | 10/01/2024 | 10/31/2024 | QA Team | 65,000.00 | 63,850.00 | +1,150.00 | On Track | Low | None required
Deployment & Go-Live | 11/01/2024 | 11/30/2024 | Operations Team | 50,000.00 | 49,500.00 | 500 | On Track | Low | Final cost verification
Total Budget Allocated |  |  |  |  | 730,000.00 | 723,975.00 | +6,025.00 | Overall Cost Performance