## Worksheet
Task | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance (USD) | Status | Responsible Party
Project Initiation | 2024-01-01 | 2024-01-15 | $50,000 | $48,500 | $1,500 (Under) | On Track | Project Manager
Feasibility Study | 2024-01-16 | 2024-02-05 | $35,000 | $34,800 | $200 (Under) | On Track | Finance Director
Design Phase | 2024-02-06 | 2024-03-31 | $150,000 | $147,650 | $2,350 (Under) | On Track | Design Lead
Development & Testing | 2024-04-01 | 2024-06-30 | $450,000 | $438,950 | $11,050 (Under) | On Track | Engineering Team
Deployment & Go-Live | 2024-07-01 | 2024-07-31 | $75,000 | $73,250 | $1,750 (Under) | On Track | Operations Manager