## Worksheet
Task | Start Date | End Date | Responsible | Budget Allocation (USD) | Actual Spend (USD) | Status | Variance (%)
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | Alex Morgan | 5,000 | 4,800 | On Track | -4.0%
Requirement Gathering | 2024-03-16 | 2024-04-10 | Sara Patel | 8,000 | 7,950 | On Track | -0.6%
Design & Prototyping | 2024-04-11 | 2024-05-30 | Jordan Lee | 12,500 | 11,800 | On Track | -5.6%
Development Phase | 2024-06-01 | 2024-08-15 | Team A (Freelancers) | 45,000 | 43,200 | On Track | -3.9%
Testing & QA | 2024-08-16 | 2024-09-10 | Mia Chen | 7,500 | 7,450 | On Track | -0.6%
Deployment & Training | 2024-09-11 | 2024-09-30 | David Kim | 6,000 | 5,950 | On Track | -0.8%