## Worksheet
Activity | Start Date | End Date | Responsible Party | Budget Allocation ($) | Cost Variance | Status
Project Initiation | 01/01/2024 | 01/15/2024 | Project Director | 50,000 | $0.00 | On Track
Scope Finalization | 01/16/2024 | 02/15/2024 | Business Analysts | 65,000 | $1,200 Over | Monitoring
Design & Prototyping | 02/16/2024 | 04/15/2024 | Design Team | 120,000 | $5,800 Under | On Track
Development Phase | 04/16/2024 | 07/15/2024 | Engineering Team | 300,000 | $15,000 Over | At Risk
Testing & QA | 07/16/2024 | 08/15/2024 | QA Department | 45,000 | $0.00 | On Track
Deployment & Go-Live | 08/16/2024 | 08/31/2024 | IT Operations | 30,000 | $2,500 Under | On Track