## Worksheet
Month | Project Phase | Budget Allocation ($) | Actual Spend ($) | Variance ($) | Status | Reserve (%)
January | Feasibility Study & Requirements Gathering | 25,000 | 23,500 | +1,500 (Under Budget) | On Track | 5%
February | Design & Feasibility Validation | 30,000 | 29,800 | +200 (Under Budget) | On Track | 3%
March | Development Phase - MVP | 60,000 | 58,200 | +1,800 (Under Budget) | On Track | 4%
April | Testing & Quality Assurance | 40,000 | 39,600 | +400 (Under Budget) | On Track | 2%
May | Deployment & Go-Live | 50,000 | 52,100 | -2,100 (Over Budget) | At Risk | 8%
June | Post-Deployment Review & Optimization | 20,000 | 19,500 | +500 (Under Budget) | On Track | 3%