## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Budget Allocation (USD) | Actual Spend (USD) | Variance (USD) | Status
Feasibility Study | 2024-03-01 | 2024-03-15 | Project Planning Team | 50,000.00 | 48,750.00 | +1,250.00 | On Track
Design Development | 2024-03-16 | 2024-05-31 | Engineering & Design Team | 150,000.00 | 147,350.00 | +2,650.00 | On Track
Procurement & Sourcing | 2024-06-01 | 2024-07-30 | Purchasing & Logistics Team | 180,000.00 | 185,250.00 | -5,250.00 | At Risk
Construction & Implementation | 2024-08-01 | 2024-11-30 | Operations & Construction Team | 750,000.00 | 738,950.00 | +11,050.00 | On Track
Testing & Commissioning | 2024-12-01 | 2025-01-31 | Quality Assurance Team | 90,000.00 | 89,650.00 | 350 | On Track
Total Budget (USD) |  |  |  | 1,120,000.00 | 1,429,950.00 | -309,950.00 | Overall Status: Over Budget (Adjustment Required)